## Sheet1
Phase | Phase Name | File/Component | Change Type | Description | Status | Completed At | Test Result | Notes
Init | Report Initialization | change_report.xlsx | NEW | Created initial tracking report | ✅ Complete | 2026-09-23 18:33:11 |  | Infrastructure setup
Task 1 - Phase 1A | PHP 8.3 Upgrade | Laragon PHP Configuration | CONFIG | User upgraded Laragon CLI to PHP 8.3 | ✅ Complete | 2026-09-23 18:46:55 |  | Manual setup by user
Task 1 - Phase 1B | Laravel 11 to 12 | composer.json | MODIFY | Upgraded dependencies to Laravel 12.0 | ✅ Complete | 2026-09-23 18:47:00 | PASS | Run via composer update -W
Task 1 - Phase 1C | Laravel 12 to 13 | composer.json & .env | MODIFY | Upgraded dependencies to Laravel 13.0 and added .env prefixes | ✅ Complete | 2026-09-23 16:53:37 | Partial (Some Auth Tests Failed) | Laravel 13.33.0 installed
Phase 2 | Data Migration (Categories, Products, Images, Inventories) from Bagisto (punjabimandi_old) to New DB (punjabimandi) | SUCCESS |  |  |  | 2026-09-23 17:18:52
Phase 3 | Rebranding: Replaced Indian Punjabi Bazaar with Punjabi Mandi, ipbgrocery.com with punjabimandi.com | SUCCESS |  |  |  | 2026-09-23 17:24:49
Phase 4 | Homepage Logo & Menu Flyout | header.blade.php, partial-category.blade.php | FIX | Fixed oversized logo and prevented 'Shop By Category' dropdown from staying permanently open. | ✅ Complete | 2026-09-25 22:43:59 | SUCCESS | Resolved layout bugs.
Phase 5 | Product Details Null Handling | product-details.blade.php | FIX | Filtered out literal '<p>null</p>' values from database for product descriptions, benefits, and ingredients. | ✅ Complete | 2026-09-25 22:43:59 | SUCCESS | Used strip_tags and trim.
Phase 6 | Vue Hardcoded URLs | BookATime.vue | FIX | Replaced hardcoded 'punjabimandi.com' URLs with relative paths and compiled JS assets. | ✅ Complete | 2026-09-25 22:43:59 | SUCCESS | npm run build executed.
Phase 7 | Checkout Workflow & SMTP | CheckoutController.php, PaymentController.php | FIX | Wrapped sendInvoice in try-catch to prevent SMTP failure from crashing checkout. Added payment error page. Set new orders to 'processing'. | ✅ Complete | 2026-09-25 22:43:59 | SUCCESS | Created payment/failed.blade.php.
Phase 8 | Homepage Banner Layout | sliders.blade.php, index.blade.php, style.css | FIX | Made banner 100% full width edge-to-edge. Removed 600px height limit to prevent cropping. Fixed horizontal scroll by positioning carousel arrows internally. | ✅ Complete | 2026-09-25 22:43:59 | SUCCESS | Removed invalid nested layout.
Phase 9 | Customer Login Redirect | CustomerController.php | FIX | Filtered 'url.intended' session variable to prevent redirecting customers to the admin login page upon successful login. | ✅ Complete | 2026-09-25 22:43:59 | SUCCESS | Added str_contains admin check.
2026-10-01 03:24:04
2026-10-01 23:08:47
2026-10-02 20:15:02
2026-10-02 20:15:09
2026-10-04 20:15:59
2026-10-04 20:16:03
2026-10-05 02:30:49
2026-10-05 02:30:53
2026-10-06 20:12:00
2026-10-06 20:13:42
2026-10-07 15:46:30
2026-10-07 16:37:36
2026-10-08 21:40:06
2026-10-08 21:40:39
2026-10-10 07:39:45
2026-10-10 07:39:52
2026-10-10 22:30:19
2026-10-10 22:30:23
2026-10-11 02:26:30
2026-10-11 08:16:35
2026-10-12 19:48:28
2026-10-12 19:49:27
2026-10-13 05:56:12
2026-10-14 18:53:28
2026-10-14 18:53:51
2026-10-16 21:06:03
2026-10-16 21:06:13
2026-10-18 23:36:57
2026-10-18 23:37:04
2026-10-19 17:53:03
2026-10-19 18:42:50
2026-10-19 18:43:03
2026-10-20 10:06:10
2026-10-20 10:06:35
2026-10-20 15:30:44
2026-10-20 21:01:58
2026-10-20 21:02:38
2026-10-21 12:37:10
2026-10-22 19:01:15
2026-10-22 19:32:10
2026-10-22 19:32:17
2026-10-24 15:43:00
2026-10-24 15:43:48
2026-10-24 21:34:16
2026-10-24 21:34:19
2026-10-25 10:45:29
2026-10-25 22:10:43
2026-10-26 21:28:00
2026-10-26 21:28:57
2026-10-27 18:37:25
2026-10-28 18:23:40
2026-10-28 20:02:08
2026-10-28 20:02:49
2026-10-30 19:59:53
2026-10-30 19:59:55
2026-10-30 22:44:08
2026-10-31 06:16:52
2026-11-01 20:08:42
2026-11-01 20:09:09
2026-11-02 01:32:42
2026-11-02 04:57:46
2026-11-02 04:59:34