## Sheet1
Phase Name | File/Component | Change Type | Description | Status | Completed At | Test Result | Notes
PHP 8.3 Upgrade | Laragon PHP Configuration | CONFIG | User upgraded Laragon CLI to PHP 8.3 | ✅ Complete | 2026-09-23 | SUCCESS | Manual setup by user
Laravel 11 to 12 | composer.json | MODIFY | Upgraded dependencies to Laravel 12.0 | ✅ Complete | 2026-09-23 | SUCCESS | Run via composer update -W
Laravel 12 to 13 | composer.json & .env | MODIFY | Upgraded dependencies to Laravel 13.0 and added .env prefixes | ✅ Complete | 2026-09-23 | SUCCESS | Laravel 13.33.0 installed
Data Migration (Categories, Products, Images, Inventories) from Bagisto (punjabimandi_old) to New DB (punjabimandi) | SUCCESS |  |  | ✅ Complete | 2026-09-24 | SUCCESS
Rebranding: Replaced Indian Punjabi Bazaar with Punjabi Mandi, ipbgrocery.com with punjabimandi.com | SUCCESS |  |  | ✅ Complete | 2026-09-25 | SUCCESS
Homepage Logo & Menu Flyout | header.blade.php, partial-category.blade.php | FIX | Fixed oversized logo and prevented 'Shop By Category' dropdown from staying permanently open. | ✅ Complete | 2026-09-26 | SUCCESS | Resolved layout bugs.
Product Details Null Handling | product-details.blade.php | FIX | Filtered out literal '<p>null</p>' values from database for product descriptions, benefits, and ingredients. | ✅ Complete | 2026-09-26 | SUCCESS | Used strip_tags and trim.
Vue Hardcoded URLs | BookATime.vue | FIX | Replaced hardcoded 'punjabimandi.com' URLs with relative paths and compiled JS assets. | ✅ Complete | 2026-09-26 | SUCCESS | npm run build executed.
Checkout Workflow & SMTP | CheckoutController.php, PaymentController.php | FIX | Wrapped sendInvoice in try-catch to prevent SMTP failure from crashing checkout. Added payment error page. Set new orders to 'processing'. | ✅ Complete | 2026-09-27 | SUCCESS | Created payment/failed.blade.php.
Homepage Banner Layout | sliders.blade.php, index.blade.php, style.css | FIX | Made banner 100% full width edge-to-edge. Removed 600px height limit to prevent cropping. Fixed horizontal scroll by positioning carousel arrows internally. | ✅ Complete | 2026-09-27 | SUCCESS | Removed invalid nested layout.
Customer Login Redirect | CustomerController.php | FIX | Filtered 'url.intended' session variable to prevent redirecting customers to the admin login page upon successful login. | ✅ Complete | 2026-09-27 | SUCCESS | Added str_contains admin check.
Bug Fixes & Maintenance | Customer Login Flow | FIX | Fixed a bug where customers were sometimes redirected to the wrong page after successfully logging in. | ✅ Complete | 2026-09-28 | SUCCESS | Improves user experience.
Bug Fixes & Maintenance | Promotional Banners | FIX | Resolved an issue with promotional banners to ensure they display correctly. | ✅ Complete | 2026-09-28 | SUCCESS | Restored visibility of offers.
Bug Fixes & Maintenance | Payment Failure Experience | NEW | Fixed a payment gateway issue and implemented a dedicated Payment Failed UI page so customers have clear instructions if a transaction is declined. | ✅ Complete | 2026-09-28 | SUCCESS | Better error handling for payments.
Order Flow Enhancements | Cart Summary Accuracy | FIX | Resolved an issue with the shopping cart summary and improved the overall order processing flow for both the customer and store administrator. | ✅ Complete | 2026-09-29 | SUCCESS | Ensures accurate order totals.
Order Flow Enhancements | Order & Invoice Formatting | NEW | Generated formal Order Numbers and Invoice Numbers, securely stored them in the system, and updated the website and email templates to display them clearly with a # prefix. | ✅ Complete | 2026-09-29 | SUCCESS | More professional invoice formatting.
Order Flow Enhancements | Order Cancellation | FIX | Fixed a bug in the Customer User Panel to ensure customers can successfully cancel their orders without errors. | ✅ Complete | 2026-09-30 | SUCCESS | Restores customer self-service cancellation.
New Design Foundation | Global Design | NEW | Applied the new modern design theme (colors, fonts, icons) across the entire website foundation. | ✅ Complete | 2026-10-01 | SUCCESS | Sets the stage for all new pages.
New Design Foundation | Header & Navigation | NEW | Implemented the new top header containing the logo, main navigation menu, search bar, and user account links. | ✅ Complete | 2026-10-01 | SUCCESS | Improved mobile and desktop navigation.
New Design Foundation | Footer Section | NEW | Built the new website footer with company information, quick links, and social media connections. | ✅ Complete | 2026-10-01 | SUCCESS | Standardized across all pages.
New Design Foundation | Search Dropdown | NEW | Enhanced the search bar to show live product results in a dropdown menu without leaving the page. | ✅ Complete | 2026-10-01 | SUCCESS | Includes quick add-to-cart buttons.
New Design Foundation | Product Display Cards | NEW | Created the new standard product display card showing product image, price, sale badges, and add-to-cart button. | ✅ Complete | 2026-10-01 | SUCCESS | Used consistently across the site.
Home Page Redesign | Main Banner Slider | NEW | Added a large, rotating promotional banner at the top of the home page. | ✅ Complete | 2026-10-02 | SUCCESS | Automatically cycles through offers.
Home Page Redesign | Shop by Category | NEW | Added a visually appealing circular grid to help customers quickly browse main categories. | ✅ Complete | 2026-10-02 | SUCCESS | Scrollable on mobile devices.
Home Page Redesign | Trust Badges | NEW | Added an information strip highlighting fast delivery, quality guarantees, and secure payments. | ✅ Complete | 2026-10-01 | SUCCESS | Builds customer trust.
Home Page Redesign | Popular Products | NEW | Added a carousel section to showcase featured and highly sought-after products. | ✅ Complete | 2026-10-01 | SUCCESS | Swipeable product list.
Home Page Redesign | Hot Categories | NEW | Created a tabbed section allowing users to switch between different top categories instantly. | ✅ Complete | 2026-10-02 | SUCCESS | Displays products per category tab.
Home Page Redesign | Promotional Banners | NEW | Integrated sections for medium-sized promotional images to highlight specific sales or collections. | ✅ Complete | 2026-10-02 | SUCCESS | Supports single and dual banner layouts.
Home Page Redesign | Bestsellers & New Arrivals | NEW | Added dedicated scrolling carousels for top-selling items and newly added inventory. | ✅ Complete | 2026-10-01 | SUCCESS | Automatically updates based on store data.
Home Page Redesign | Customer Reviews | NEW | Implemented a sliding testimonials section to display positive customer feedback. | ✅ Complete | 2026-10-02 | SUCCESS | Shows star ratings and comments.
Home Page Redesign | Brand Showcase | NEW | Added a scrolling logo bar to feature popular brands sold on the store. | 🔄 In Progress | 2026-10-02 | PARTIAL | Continuous scrolling effect.
Home Page Redesign | About Us Summary | NEW | Added a brief company introduction section near the bottom of the home page. | ✅ Complete | 2026-10-02 | SUCCESS | Explains the store's mission.
Cart Experience | Slide-out Mini Cart | NEW | Replaced the old cart page with a modern side-panel that slides out when clicking the cart icon. | ✅ Complete | 2026-10-03 | SUCCESS | Users can review cart without leaving their current page.
Cart Experience | Cart Interactions | MODIFY | Users can now change item quantities, remove items, and see live total updates instantly. | ✅ Complete | 2026-10-03 | SUCCESS | No page refreshes required.
Cart Experience | Coupon Integration | NEW | Added the ability for customers to apply or remove discount codes directly within the mini-cart panel. | ✅ Complete | 2026-10-03 | SUCCESS | Instant discount calculation.
Cart Experience | Branding Consistency | FIX | Adjusted the shopping cart buttons and accents to perfectly match the Punjabi Mandi green branding. | ✅ Complete | 2026-10-03 | SUCCESS | Consistent visual identity.
Cart Experience | Remove Confirmation | NEW | Added a polite confirmation popup when a user tries to remove an item from their cart. | ✅ Complete | 2026-10-03 | SUCCESS | Prevents accidental deletions.
Product Listings | Category Page Layout | NEW | Completely redesigned the category browsing pages with a clean, modern layout. | ✅ Complete | 2026-10-03 | SUCCESS | Includes breadcrumb navigation.
Product Listings | Left Sidebar Menu | NEW | Added a collapsible side menu showing all store categories for easy navigation. | ✅ Complete | 2026-10-03 | SUCCESS | Highlights the current category.
Product Listings | Advanced Filtering | NEW | Implemented powerful sidebar filters allowing users to narrow products by Brand, Price, and Deals. | ✅ Complete | 2026-10-03 | SUCCESS | Checkbox selection system.
Product Listings | Grid & List Views | NEW | Added buttons allowing customers to switch between a grid view (images) and a list view (details). | ✅ Complete | 2026-10-03 | SUCCESS | Remembers user preference.
Product Listings | Product Sorting | NEW | Added a dropdown to quickly sort products by Name, Price (High/Low), and Newest arrivals. | ✅ Complete | 2026-10-03 | SUCCESS | Works alongside active filters.
Product Listings | You Might Like Section | NEW | Added a scrolling list of recommended products at the bottom of the category page. | ✅ Complete | 2026-10-03 | SUCCESS | Encourages additional discoveries.
Product Listings | Improved Pagination | NEW | Redesigned the page number navigation at the bottom of long product lists to be more user-friendly. | ✅ Complete | 2026-10-03 | SUCCESS | Shows total item counts.
UI Polish | Mobile Search Bar | WIP | Enhancing the search bar on mobile devices so it remains accessible as the user scrolls. | 🔄 In Progress | 2026-10-05 | PARTIAL | Finalizing visual appearance.
UI Polish | Mobile Product Grid | FIX | Fixed an issue where products appeared too large on mobile; restored a clean 2-column grid. | ✅ Complete | 2026-10-06 | SUCCESS | Matches the approved design.
UI Polish | Mobile Filter Menu | FIX | Completely rebuilt the mobile filter menu to slide out smoothly from the side of the screen. | ✅ Complete | 2026-10-06 | SUCCESS | Replaced a broken popup window.
UI Polish | Mobile Navigation Menu | FIX | Corrected the behavior of the mobile Hamburger menu so it opens and closes reliably. | ✅ Complete | 2026-10-05 | SUCCESS | Smooth sliding animation.
UI Polish | General Layout Fixes | FIX | Resolved various spacing, text alignment, and visual glitches across the Home and Category pages. | ✅ Complete | 2026-10-04 | SUCCESS | Ensures a premium feel.
UI Polish | Favicon & Branding | MODIFY | Updated the browser tab icon (favicon) to feature the new Punjabi Mandi branding. | ✅ Complete | 2026-10-04 | SUCCESS | Small but important detail.
New UI Implementation | Product Page | Bug Fix | Product page responsive issue fixing | ✅ Complete | 06-10-2026 | SUCCESS | Fixed UI issues on mobile devices
New UI Implementation | Wishlist / Product Page | Feature | Wishlist implementation using AJAX without page freezing, and styling updated | ✅ Complete | 06-10-2026 | SUCCESS | Wishlist icon turns red and maintains yellow background
New UI Implementation | Mobile Menu (Header) | Feature | Wishlist count implemented for mobile view in the left menu | ✅ Complete | 06-10-2026 | SUCCESS | Count dynamically updates alongside desktop using AJAX